## Slide 1
Aug
Reviewed Design Engineer Proposal
Authorize Ground water Engineer to proceed with feasibility for injection
Identified preferred sites for additional review
Sep
Public Information Discussion re: Preferred sites for additional review
Selection of Design Eng.
Oct
Initiate Environmental Review
Continue plant site review
Nov
Complete Site review (??)
Initiate retention of Assessment Engineer
Dec
Select Assessment Engineer
Select Package Plant Manufacturer
Initiate Development of Financing Plan
Jan
Feb
Groundwater Engineer Report on Disposal
Engineer- Preliminary Project Design & Cost estimate
Mar
Order Assessment Engineers Report
First Phase of Env. Review Completed
Apr
May
Consider Engineers Report
Adopt Resolution of Intent
Mail and Post Public Hearing Notice
Jun
Conduct Public Hearing
Complete Assessment Vote Process
6-28-22
Jul
Los Olivos CSD 2021/22 Working Timeline
to Benefit Assessment Vote
09.16.21 Update